## 11.07.2023
FIFE COUNCIL
TRANSPORTATION SERVICES
MINUTES of FIFE RAUC MEETING
Tuesday 11th July 2023 via TEAMS
PRESENT
| Maggie Baird (MB) |  | Fife Council Network Management NRSWA (North) Chair
| Julie Carnell (JC) |  | Fife Council Network Management NRSWA (South)
| Linda Roeleveld (LR) |  | Fife Council Network Management NRSWA
| Colin Heggie (CH) |  | AMEY
| Michael Gray (MG) |  | AMEY
| David Ross (DR) |  | BEAR
| David Murdoch (DM) |  | Network Rail
| Joanne Wilcox (JW) |  | NEOS
| Allan Pryde (AP) |  | Openreach
| Ian Dalrymple (ID) |  | Openreach
| Ian Fleming (IF) |  | Scottish Power
| Darren Pointer (DP) |  | Scottish Water
| Emma West (EW) |  | Scottish Water
| Lora Bailey (LB) |  | SGN
| Maxine Biret (MaxB) |  | SGN
| Tom Wardlaw (TW) |  | Stagecoach
| Karyn Davidson (KD) |  | Vodafone
1 | APOLOGIES AND INTRODUCTIONS
| 1.1 | MB welcomed everyone to the meeting.
| 1.2 | Apologies were received from:
Sara Wilson, Ian Jones (Fife Council), Adrian Henzler (Openreach), Julie Greig (SGN) Lorraine Jones, Craig Graham (Sottish Power) Jimmy Wilson (NEOS),Sharon Burns (Go Fibre)
2 | Minutes of previous meeting held on 11th April 2023
| 2.3 | Item 4.2
JC advised new Inspector in Mid/South - Steve Clark. Inspectors areas and contact details to be circulated with the Minutes. JC advised awaiting new Inspectors as Paul Adams and Steve Clark had left. Iain Urquhart would continue covering North area and Jim Dewar covering South area.
3 | Co-ordination of Roadworks
| 3.1 | ROAD AUTHORITY
Item 3.1.1 North
B9129 Commercial Cres, Ladybank 7 days - 11th to 19th September
B941 Largoward to Peat Inn 10 days 24th July to 4th August
B941 from A915 Largoward to B942 7th to 11th August
B940 from A915 to Peat Inn January, 2024
B940 North of Baldinnie Loan January 2024
St Marys Lane, Newport 10 days 18th to 29th September
Millfield Place, Freuchie 10 days 2nd to 13th October
B939 Craigrothie to Ceres patching, no dates as yet
B921 Kinglassie Road, Glenrothes 24 days November/December
A917 Balchrystie to Elie 20 days 18th December, 2023 to 24th January, 2024
A913 Balgarvie Road, Cupar 19 days January/February, 2024
Developer works:
A919 Guardbridge, Persimmon drainage , 20 weeks duration, dates TBC.
A911 Glenrothes - Leven Persimmon new RA ongoing end date 30th September, 2023
Hepburn Gardens, St Andrews - Barratt Homes new RA, 16 weeks duration, dates TBC.
Golf Place, St Andrews - Robertson R&A refurb ongoing to March 2024
Contact MB if any issues.
Item 3.1.2 South
Lauder College r/a Halbeath Road, Dunfermline 31st July to 18th August, contraflow
Lynebank r/a, Halbeath Road, Dunfermline 21st to 25th August, TTL
St Margarets Way, Rosyth - August to October, TTL. With road closure Milne Way
Esplanade, Kirkcaldy works ongoing until 11th August
Contact JC if any issues.
Item 3.1.3 Events:
UCI Men's World Championship Cycle race Sunday 6th August 2023. All affected roads listed on SRWR. Embargoes will be in place. Routes affected Port of Rosyth. Ferrytoll Road, Hilton Road. A985. B9037 through Torryburn. C5 through Culross back onto A985 to A977 Clackmannanshire bridge.
Walker Cup, St Andrews 28th August - 3rd September
Dunhill Cup, St Andrews 2nd to 9th October
Utilities please be aware, contact JC or MB if any issues.
| 3.2 | Item 3.2.1 BEAR
A985 Longannet,Blairhall & Kincardine, UCI embargo 27th July to 15th August
Queensferry Crossing 18th and 19th August, 50mph limit. Work has commenced on the barriers between FRB and QFC
| 3.3 | Item 3.3.1 AMEY
A92 Kilmany northbound lane closure 24th July to 7th August
A92 to Perth embargo - UCI
A92t e/b Crossgates Interchange on-slip from Crossgates Interchange 11th to 13th August
A92t e/b from Halbeath r/a to Crossgates r/a 11th to 13th August
A92 t N/B from B969 jct to New Inn r/a - cycle route 13th to 25th July
M90t s/b from jct.5 to Fife Council boundary 17th July to 3rd August
A92t from C64 to U047 jct. (Kilmany) - resurfacing 24th to 31st July
A92t from C64 to U047 jct. (Kilmany) - resurfacing 24th to 31st July
A92t from C64 to U047 jct. (Kilmany) - 31st July to 8th August
A92t e/b from Lochgelly Interchange to Chapel Interchange 7th to 8th August
A91t w/b from Chapel Interchange to Lochgelly Interchange 7th to 8th August
A92t n/b from Old Mill Road Overpass to Blackwood Road Overpass 21st August to 1st September
Major scheme at Bankhead subject to discussion once dates confirmed
Day to day patching and minor schemes will be added to SRWR and mainly take place overnight
| 3.4 | Item 3.4.1 SGN
All works on the SRWR including potential works.
Item 3.4.2 SGN Hydrogen project
SGN advised that after some issues on site project is progressing well.
Item 3.4.3 Scottish Power
All works on the SRWR
MB commented A91 Cupar to St Andrews SP, major upgrade. Utilities be aware as this will cause major disruption - Spring 2024
MB advised SP cable upgrade Leslie to Blackwood Road, issues with private land along the route. Engineers are looking at what the alternative will be. Date TBC.
IF advised he was unaware of the work but will speak with planners to ensure him and LJ are kept up to date.
Item 3.4.4 Network Rail
Elm Park, Leven - bridge works, 21st August for 1 week
All other works on the SRWR.
Item 3.4.5 Scottish Water
EW commented all works on the SRWR
|  | DP major works Pittenweem will require meeting with MB to agree dates. |  | DP/MB
Item 3.4.6 Openreach
All works on the SRWR
Item 3.4.7 Vodafone
All works on the SRWR
Item 3.4.8 NEOS
All works on the SRWR
Item 3.4.9 Virgin Media
All works on the SRWR
4 | Performance Inspection Figures
| 4.1 | All good - Cat A's, Cat B's & Cat.C's over 90%
Virgin Media issues with sample A's - 6 inspections of which 3 failed. Monitor for any recurring issues
5 | Safety/Traffic Management
| 6.1 | MB raised the issue of Road Closure applications, as part of the assessment process FC will liaise with the applicant if there are any issues however, wondered what consideration is given by the applicant as to the impact on the community where closures are necessary, is any consideration given to what alternatives may need to be considered i.e. working hours, bus services etc. at the application stage? IF commented, SP outsources to TM companies who will then survey the site. MB riased issue regarding letter drops not being carried out and requested letter drops are done even when using parking restrictions as this can impact scheduling for deliveries etc. particularly where businesses are affected. ID commented they are aware there are issues with their TM provider across Scotland with lack of relevant information being submitted with the applicatons. This is something they are currently trying to address with them.
| 6.2 | SW works Bus Station Chapel Street, Dunfermline - JC advised road closure would be granted if working overnight, this was refused by Utility. JC commented that this ties in with the discussion above, that sometimes it is not always possible to complete works during the day or weekdays and it needs to be given consideration when applying for RCs. JC requested a site meeting to look at what can be achieved outwith normal hours. In the meantime application refused.
6 | Local Issues
| 6.1 | MB mentioned that the inspectors have been asked to keep track on repetative issues they are coming across to establish if there are patterns with particular issues or companies in an effort to help improve communication and performance. A few issues that are cropping up are incomplete and incorrect contact details on forms and wrong contacts on the SRWR. Forms will be returned/refused which leads to works being delayed. The group asked that if issues are cropping up can the relevant NRSWA reps be informed at the time of incident, this helps them to ensure it is dealt with in a timely manor.. MB advised the inspectors have been asked to do this but will reiterate to them. MB advised they will continue to keep track of issues over the next couple of quarters to identify if there is a pattern and feedback information where required.
7 | AOCB
| 7.1 | CH (AMEY) requested FC programme of litter picking and sweep cleaning. AM to forward same. MB will speak to Archie Melville. |  | AM/MB
| 7.2 | Allan Pryde new representative for Openreach requested meeting with FC staff to meet and greet. MB commented that we do not have a full compliment of staff at the moment but will try and arrange something soon with relevant people. |  | MB
8 | FUTURE MEETINGS
| 8.1 | Tuesday 10th October, 2023
Tuesday 9th January, 2024
Circulate to those attending the meeting, those who gave apologies and:-
John Mitchell, FC Senior Manager - Roads and Transportation Services

## North Area Works
B941 from A915 – B942 June 2023 exact date TBC
B941 from Largoward – Peat Inn June 2023 exact date TBC
B940 from A915 – Peat Inn June 2023 exact date TBC
B940 North of Baldinnie Loan June 2023 exact date TBC
Potential conflict on the above schemes with Scottish Water MB to send CMcQ the plans - Action complete
A914 Kettlebridge – Balmalcolm Date TBC
A919 from A91 Guardbridge RA to Toll Road – October school holidays dependant on developer works
B921 from Kinglassie Road – B922 5th June – 16th June
C1 Kennoway Road, Leven 7th – 18th August
A915 Standing Stane Road nightshift 28th May – 1st June
A916 Sandy Brae, Kennoway date TBC
A917 from Balchrystie – Elie 18th December – 26th January
A913 Balgarvie Road Cupar 29th January – 23 February
All of the above are carriageway schemes any questions please contact MB
Developer Works
A911 Construction of new roundabout. Persimmon Homes commences 15th May. Temp 2 way lights off peak for 1 week to construct temp running lane then 2 way traffic will be maintained for the majority of the project before returning to a short period of lights off peak for completion.
A919 new sewer Persimmon Homes date TBC
St Andrews LLP Petheram Car Park off the A91 1st May – 31st May